## Sheet1
Date | Hours | User Story | Description
2017-04-17 | 1.5 | UI | Fixed some of the stuff per Prof Sedlemeyer's comments on UI
2017-04-18 | 3 | TopTen.txt | Changed the way we save top scores to a text file
2017-04-19 | 3 | SF-17 | Almost finished everything for this user story. All that is left is a sort method for the model
2017-04-20 | 1 | SF-17 | Created the sort method and properly implemented it
2017-04-20 | 1.5 | SF-17 | Added the date to both top ten lists
2017-04-20 | 1 | SF-13 | Added a button that will remove all tiles of a number based on user input
2017-04-23 | 1 | SF-13 & SF-14 | Made the changes for the limit on how often you can use these features